## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 29.03.2022, 19:30
Group Number |  | 21
Participant 1 |  | Loisel Andrija
Participant 2 |  | Reynaud Cade
Participant 3 |  | Stadler Alexander
Participant 4 |  | Dragnev Laurenz
Participant 5 |  | Wograndl Raoul Christian
Mentor |  | Richter Georg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Creating basic project structure | 5 | 4 | -1 |  |  | Zusammen mit der organisatorischen Herausforderung, Git und Github einzurichten, hat das Erstellen der Projektstruktur relativ viel Zeit in Anspruch genommen (Done)
2 | Implementing basic HTML stucture | 15 | 4 | -11 |  |  | Wir haben erstmals ein paar Templates für die index.html Seite erstellt, die später noch verändert werden können (WiP)
3 | Creating basic CSS stylesheet | 15 | 2 | -13 |  |  | Das Ändern von Bootstrap Eigenschaften ist mit dem Bearbeiten vom Source Code verbunden, aus diesem Grund belassen wir vorerst es bei Vanilla Bootstrap (WiP)
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -25 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol