## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2022-05-03 22:00
Group Number |  | 21
Participant 1 |  | Loisel Andrija
Participant 2 |  | Reynaud Cade
Participant 3 |  | Stadler Alexander
Participant 4 |  | Dragnev Laurenz
Participant 5 |  | Wograndl Raoul Christian
Mentor |  | Richter Georg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Loginsystem erstellen | 21 | 15 | -6
2 | Levelsystem erstellen | 13 | 13 | 0
3 | Loginprofil erstellen, Profildaten ändern | 15 | 10 | -5
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -11 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol