## Tabelle1
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 2022-06-14 19:00
Group Number |  | 21
Participant 1 |  | Loisel Andrija
Participant 2 |  | Reynaud Cade
Participant 3 |  | Stadler Alexander
Participant 4 |  | Dragnev Laurenz
Participant 5 |  | Wograndl Raoul Christian
Mentor |  | Richter Georg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Freundesliste um Level der Freunde und Highscores ergänzt | 1 | 2.5 | 1.5
2 | Sortieren der Freundesliste erweitert um Level und Highscores | 1 | 2 | 1
3 | CSS/Design der Freundesliste abgeändert | 1 | 1 | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 2.5 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol